## Sheet1
Karui Changes		Details
Cubed volume	Yes	Currently 286mm cube	Done
Internal PS	Yes	Meanwell 500W – Switch mounting in case for the 500W
Integrated LCD	Yes
Move Plugs to back and Fan	Yes	Plugs good, move fan
Auto-leveling	Yes	Need to test on TAZ size printer
0.50 Nozzle	Yes	Already integrated into TAZ line	Done
Dual Extrusion Fans	Yes	We just need to make sure splicing the fans together is a good way to go here	Done
Cable guides	Yes	Larger may be necessary	Done
Stainless Drive rods	Yes	Testing multiple options here
Quieter	Yes	Higher micro stepping, cork if needed, quieter fans
Better wiper / lower	Maybe	If there is a z backup switch, this can't be lower
Min and Max switches	Yes		Done
New Extruder	Maybe	Something without spring screws and a significantly easier latch
Stiffer Axis for droop/bed warp	Yes	Maybe horizontal X axis bars, balance Extruder over bars
New Bushings/linear bearings	Maybe	Less slop in system from bushings
New Drive system in Z	Maybe	Floating Drive, better control on smooth rods, belts

Injection molded parts	Yes	Should design plastic parts with this in mind
Filament cleaner/wiper	Yes	Integrated onto spinner maybe
Change the drive gear material	Maybe	molded or switch to nylon possibly
Cleaner/easier wiring	Yes	make wire harnesses easier to build. Don't combine multiple into one if possible

New Board	Yes	New layout is needed after FCC testing
New LCD	Maybe	Need to shop around and test these with new board
Z-Backup switches	Yes	Firmware will be the hardest part of this one. We have the switch and the location on the board
No “back-power” to LCD when bed moves	Yes	In progress with the new board testing
FCC/CE	Yes	Class B with new board and PS
New LCD Menu structure	Yes

New Box	Yes	Something more conducive to retail shelving
New Name	Yes	TAZ 6
New Laser etching	Yes
Change the Look	Yes
Less expensive	Yes
Easier to Assemble for customer	Yes	30 min box to print?
Easier to Assemble for manufacturing	Yes
Change Switch color	Maybe	Red and Green are easy, Yellow is possible
New document package	Yes

New Nozzle/All in one dual?	No	Maybe non-changeable, welded nozzle. Possibly all in one dual nozzle?
Thermal Fuse	No	Needs research
Lights	No	Do we need to add something onto the board for this?
Wifi module	No	Find/Test
Higher step settings	No	Testing new motor drivers