## Sheet1
		Schedule – Product Development Cycle
		03-02	03-09	03-16	03-23	03-30	04-06	05-18	05-25	06-01	06-08	06-15	06-22	06-29	07-06	07-13	07-20	07-27	08-03	08-10	08-17	08-24	08-31	09-07	09-14	09-21	09-28	10-05	10-12	10-19	10-26	11-02	11-09	11-16	11-23	11-30	12-07	12-14	12-21	12-28	01-04	01-11	01-18	01-25	02-01	02-08	02-15	02-22

TASKS	OWNER						EVT / Engineering Verification Test					Finish Ordering / DVT Parts	Wating for DVT Parts			DVT – Qualification / Design Verification Test					Finish Ordering / SAT Parts	Wating for SAT Parts			SAT – Qualification / Ship Approval Test		Production & Inventory Buildup
R&D – Mechanical
Make change list
Finish Design for EVT
Make drawing for Avon mecnical
Make EVT BOM
Finalize BOM for DVT
Finalize BOM for SAT
Get product specs to Marketing
R&D Electrical
Feature list for Avon
Connector list for Avon
New Avon layout
Design spin for any changes to board for DVT
LCD board layout
Lights
LCD menu structure
Wi-Fi module
Thermal fuse
Firmware
Software
Cura profiles
Any needed Cura changes
Build & Test
Built and test EVT printers
Test new boards
EMC test Printer with EVT Avon
EMC test with EVT printer
Final EMC testing on Production printer
Test bed leveling on TAZ
Test final firmware/software configuration
Packaging / Documentation
Foam design							6-8 weeks, additional 1-2 if there are changes
Packaging Design
User Manual
Documentation
Procurement
Camellia (DVT/SAT) Parts
Production Parts – Long lead
Order boards as many times as we need
Order parts for EVT Printers
Order parts for 20 DVT Printers
Order production samples of Boards
Order long lead production parts
Order short lead production parts
Plastic Parts
Manufacturing
Process step define (presub-FA)		1st pass
Process step layout
Assembly line layout & BOM
Mfg line 2 construction/ purchase
Resource Plan proposal/ approval
Recruiting mfg staffs
Training new team
Build 20 of the DVT printers
Build 30 of th SAT printers
Design/Build up any fixturing needs for Assembly
Build production
Assembly OHAI Kits
PreSub Op setup & production prep
Cycle time modeling		1st pass
Presub/Sub Test Defined
Pre/Sub Test Equip Des/Setup
- Harness Test Fixture
- Other fixtures
MO
Marketing / PR / Sales / CS
Final Product Photos
Product Pages
Customer support training
Product Description
Product name
EVT laser etch concept
Printers for review
Product name for new board